## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus hours
Setup | 0.1 | 2024-07-11 | Created Vue project, read documents and started setting up timer, IDE, browser
US01 | 0.9 | 2024-07-11 | Created navbar component, implemented vue-router library, styled navbar elements, set routing elements
US02 | 1 | 2024-07-11 | Started the API component with the method to get all houses
US02 | 1.5 | 2024-07-12 | Finished to set the API and styled the cards for the house listings
US03 | 3.7 | 2024-07-12 | Created the Research component and linked to the array of listings, with reset button and search button. Placed image and text for the null research case and the text with the number of listings found per research
US4 | 2 | 2024-07-12 | Created sort component and linked into the HomeView code. Sort possibilities are: Price and Size
US5 | 1 | 2024-07-13 | Created the component to edit or delete a listing (EditYourListing) and called in Card component and in HouseView
US6 | 6 | 2024-07-13 | Created View component and routing methods, small fixes to overall css of HomeView elements. Create input component and linked to form. Composed form view. Added error handling for inputs.
US6 | 2.5 | 2024-07-15 | Image API methods
US8 | 0.5 | 2024-07-15 | Delete listing function created and applied to delete icons
US6 | 4 | 2024-07-15 | Route to house listing after creating it. Fixed routing to force reload after submitting form or deleting listing
US8 | 2.5 | 2024-07-16 | Created starting condition which differentiates the creation of a new listing to the editing which, in case an id is provided in the url, sets all variables to the value received via API. Fixed bugs with image input
Styling | 2.5 | 2024-07-16 | Fix to all pages according to the mockups
US9 | 0.017361 | 2024-07-16 | Fix to the method to call before deleting the listing
Dark mode |  | 2024-07-16 | Create store variables for dark mode, compoenent and linked to navbar | 1
Like mechanism |  | 2024-07-16 | Added storage rule for liked house and linked to a button added to each house listed. Al lliked houses are then shown into a liked-by-me page (added into the navbar) | 0,5
Improve components due to new views |  | 2024-07-17 | Added HousesList, in order to reduce redundancy for homepage, favourite list and my listings | 1,5
Recommended |  | 2024-07-17 | Added recommended houses, based on the same city of the selected house (same number of bedrooms is set to, but deactivated due to the few houses on the database) | 1,5
My listings |  | 2024-07-17 | Created the view and used a similar structure as MyFavouriteView, in order to avoid bugs with the routing | 0,5
Chronology |  | 2024-07-18 | Add chronology sidelist in HouseView | 0,25
Search query |  | 18?07 |  | 2
Total amount of hours | 28.2174
API key | 1owkyeAxJYWi-8EjqbgQ5IK_OLT2VGHC